## Agile Product Backlog
TRANSPORT AL AGILE PRODUCT BACKLOG SPRINT
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
1 | APP DEV SECTION | Sprint 1 | Mohammed | 2018-09-26 |  | No | No | High | In Progress |  | No
2 | Created Firebase Account | " " | " " | 2008-09-26 |  | Yes | Yes | Medium | Complete |  | Yes | This section is for the drop-down list
3 | Created Project int the firebase | " " | " " | 2018-09-26 |  | Yes | Yes | Medium | Complete |  | Yes | Yes | High | Complete
4 | Created pro. In the And std | " " | "" | 2018-09-26 |  | yes | yes | Medium | Complete |  | Yes
5 | added gradle script from the firebase | " " | "" | 2018-09-26 |  | yes | yes | Medium | Complete |  | Yes
6 | Social account signUp | " " | Rudy | 2018-09-28 |  | Yes | yes | Medium | Complete |  | Yes
7 | setup login for the Cutomer & Vehicale | " " | Mohammed | 2018-09-28 |  | Yes | Yes | Medium | Complete |  | Yes | No | Medium | In Progress
8 | map updated | " " | Rudy | 2018-09-28 |  | Yes | yes | Medium | Complete |  | Yes
9 | Location uodated | " " | " " | 2018-09-28 |  | yes | yes | Medium | Complete |  | Yes
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT |  | Low | Not Started
| BACKEDN/ ADMIN SECTION | Sprint 1
1
2 |  | Done
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
| ARDINO SECTION | Sprint 1
1 |  | Done
2
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
| APP DEV SECTION | Sprint 2
1 | Customer can call vehical | " " | Rudy | [5 empty] | In Progress
2 | See the current location for customer | " " | Rudy | [5 empty] | In Progress
3 | Map update for driver | " " | Rudy | [5 empty] | In Progress
4 | Map update for Customer | " " | Rudy | [5 empty] | In Progress
5 | PayPal payment method implemented | " " | Mohammed | [5 empty] | Completed
6 | paypal API implemented | " " | Mohammed | [5 empty] | Complete
7 | Driver/Vehical can see the history | " " | Mohammed | [5 empty] | Complete
8 | Customer can see his/her history | " " | Mohammed | [5 empty] | Complete
9 | Vehical can update its setting.name,phone number,service type, vehicale type | " " | Mohammed | [5 empty] | Complete
10 | Customer can update his/her profile-name, phone number, profile image | " " | Mohammed | [5 empty] | Complete
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
| BACKEDN/ ADMIN SECTION | Sprint 2
1 |  | Done
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
| ARDINO SECTION | Sprint 2
1 |  | Done
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
| APP DEV SECTION | Sprint 3
All features Implemented